# Evaluating Trustworthy Anomaly Detection in CDC COVID-19 Data

# Final Project Work Flow Outline

# Summary Project Goal

This project investigates how anomaly detection methods, commonly used in fraud detection systems, can be applied to large-scale public health surveillance data. Using CDC COVID-19 reporting datasets, we analyze temporal and regional reporting patterns to identify unusual observations that deviate from expected trends.

Rather than interpreting these irregularities as fraudulent behavior, the goal of this study is to evaluate how reliably anomaly detection models can detect anomalies within large-scale public health datasets.

In addition to evaluating model performance, this project emphasizes trustworthy artificial intelligence, specifically examining whether detected anomalies can be interpreted and explained in meaningful public health contexts. By combining techniques from anomaly detection, fraud detection methodologies, and public health data analytics, this project aims to assess both the effectiveness and the trustworthiness of AI-based anomaly detection systems for monitoring public health reporting data.

# Proposed Hypotheses:

# Hypothesis 1 (Primary)

Anomaly detection algorithms can identify unusual patterns in CDC COVID-19 reporting data, such as sudden spikes, drops, or irregular reporting behaviors that deviate from expected temporal trends.

# Hypothesis 2 (Model Comparison)

Different anomaly detection models will identify different sets of anomalies, reflecting variations in model sensitivity and assumptions about normal behavior.

Models may include:

~ Isolation Forest

~Local Outlier Factor (LOF)

~ One-Class SVM

# Hypothesis 3 (Trustworthiness & Interpretability)

Many detected anomalies can be interpreted and explained through real-world public health factors, such as:

~ reporting delays

~data corrections

~backlog reporting

~sudden outbreak clusters

This supports the idea that anomaly detection models can be used in a trustworthy and interpretable manner for public health surveillance.

Dataset:

# CDC COVID-19 Surveillance Data

Link:

Proposed Tools & Libraries

Python ecosystem:

Pandas – data processing

NumPy – numerical computation

Matplotlib / Seaborn – visualization

Scikit-learn – anomaly detection algorithms

# SHAP or feature importance tools – interpretability

Person A (Colyn Martin) – Data Preparation & Quality Control Lead

# Primary Responsibilities

- Obtain and organize the CDC COVID-19 dataset

- Perform basic data cleaning (handling missing values, duplicates, formatting dates)

- Ensure the dataset is consistent and ready for analysis

- Assist in creating or verifying derived variables used for analysis (daily changes, rolling averages)

# Quality Control Role

- Review model outputs to confirm they align with the cleaned dataset

- Verify that detected anomalies correspond to correct dates and locations

- Help summarize the data preparation process for the final report

Person B (Ayushi Bohra) – Anomaly Detection Modeling Lead

# Primary Responsibilities

- Implement anomaly detection algorithms in Python

● Train models such as, but not limited to:

○ Isolation Forest

○ Local Outlier Factor

○ One-Class SVM

- Run anomaly detection experiments

- Compare results across models

- Generate anomaly detection visualizations

# Secondary Role

● Work with Person A to ensure modeling features are prepared correctly

Person C (Ananya Vakde) – Analysis & Interpretation Lead

# Primary Responsibilities

- Examine anomalies detected by the models

Determine whether anomalies correspond to real-world reporting events

- Analyze patterns across states or time periods

- Evaluate how interpretable the anomaly detection results are

# Secondary Role

● Review anomaly detection outputs and visualizations to confirm interpretations are supported by the data

***** TIMELINE *****

WEEK 1 – Data Acquisition & Dataset Understanding

Person A

- Obtain the CDC COVID-19 dataset and generate a representative sample dataset for analysis

- Perform data cleaning on the sample dataset (handling missing values, formatting dates, etc.)

- Ensure the sampled dataset maintains consistency with the original dataset

- Set up the repo and document how the sample dataset was created

Person B

- Conduct initial exploratory analysis using the sampled dataset

- Examine distributions of key variables (cases, outcomes, demographics)

- Identify variables from the sampled dataset that will be useful for anomaly detection

Person C

- Research COVID reporting patterns and known reporting artifacts

- Identify possible causes of irregularities that may appear in the sampled dataset

Cross-Check

- Person B verifies that the sampled dataset preserves key distributions from the full dataset

- Person C reviews dataset documentation

- Team ensures the sampled dataset is suitable for reproducibility and modeling

WEEK 2 – Exploratory Analysis & Feature Preparation (Updated)

Person A

- Create derived features using the sampled dataset:

~ daily case changes

~ rolling averages

~ normalized case rates

Person B

- Create exploratory visualizations using the sampled dataset:

~ time-series plots

~ case distributions

~ comparisons across time

Person C

- Define criteria for identifying anomalies based on patterns observed in the sampled dataset

Cross-Check

- Ensure features and visualizations align with the sampled dataset

- Confirm that patterns observed are consistent with expected trends

WEEK 3 – Anomaly Detection Modeling (Updated) Person B

- Implement anomaly detection models using the sampled dataset

- Train models (Isolation Forest, LOF, One-Class SVM)

- Detect anomalies and compare outputs across models

Person A

- Verify that the sampled dataset used for modeling is clean and consistent

- Ensure features are correctly computed from the sample Person C

- Begin analyzing anomalies detected from the sampled dataset

- Look for patterns across time

WEEK 4 – Analysis & Interpretation (Updated) Person B

- Compare anomaly detection results across models using the sampled dataset

- Identify overlapping anomalies

Person C

- Interpret anomalies and connect them to real-world explanations:

~ backlog updates

~ outbreak spikes

~ reporting delays

Person A

- Verify anomalies correspond to valid data points in the sampled dataset

WEEK 5 – Synthesis & Presentation

Person A

- Summarize how the sampled dataset was created and validated Person B

- Present model results and anomaly visualizations based on the sampled dataset

Person C

- Summarize interpretations and real-world explanations

Entire Team

- Ensure workflow is reproducible using the sampled dataset

- Document reasoning for using a sample instead of the full dataset

- Compile final report and presentation